United Republic of Tanzania

Environmental and Social Management Plan (ESMP)

For

Tanganyika District Council

Land Tenure Improvement Project

Ministry of Lands Housing and Human Settlement Development

May, 2023

Working Team

| NAME | PROFESSION/POSITION | ORGANIZATION |
| --- | --- | --- |
| Joseph C. Bisura | Environmental Officer | Tanganyika District Council |
| Raymond Kabekenga | Social Development Officer | Tanganyika District Council |
| Alpha P. Mangula | Environmental and Social Coordinator, -LTIP | MLHHSD |
| Tumaini Setumbi | Social Development Officer -LTIP | MLHHSD |
| Robert Kishiki | Social Development Specialist - LTIP | MLHHSD |
| Regina Kabwogi | Environmental Specialist - LTIP | MLHHSD |

Table of Contents

LIST OF TABLES	iv

LIST OF FIGURES	iv

LIST OF ABBREVIATIONS AND ACRONYMS	v

CHAPTER ONE	1

INTRODUCTION	1

1.0 Background Information	1

1.1 LTIP Project Scope in Tanganyika District Council	1

1.3 General Objectives of ESMP	4

1.1.	Methodology for Preparation of ESMP	4

CHAPTER TWO	6

BASELINE ADMINISTRATIVE, ENVIRONMENTAL AND SOCIAL CONDITION OF THE PROJECT AREA	6

2.1	Introduction	6

2.2	Administrative Condition of Tanganyika District Council	6

2.3 Environmental Baseline Information in Tanganyika District Council	7

2.4 Tanganyika District Council Social Baseline Information	14

3.	CHAPTER THREE	17

LEGAL AND INSTITUTIONAL FRAMEWORK	17

3.1 Introduction	17

3.2 Country’s Legal Framework to Guide Land Use Planning and Rural Certification Processes in Tanganyika District	17

3.3 World Bank Environmental and Social Framework	20

CHAPTER FOUR	22

ENVIRONMENTAL AND SOCIAL IMPACTS, RISKS AND MITIGATION MEASURES	22

4.1 Introduction	22

4.2 Project Social Benefits	22

4.3 Negative Social Risks and Impacts of Land Use Planning and Rural Land Certification	23

4.4	Project Positive Environmental Impacts of Land Use Planning and Land Certification	24

4.5 Negative Environmental Impacts of Land Use Planning and Land Certification	25

4.6 Mitigation Measures of the Identified Impact	25

CHAPTER FIVE	36

Monitoring of Environmental and Social Impacts	36

5.1 Introduction	36

CHAPTER SIX	43

INSTITUTIONAL ARRANGEMENTS FOR IMPLEMENTATION OF ESMP	43

6.1 Institutions	43

6.2 Supervision and Monitoring Roles	44

6.4 Capacity Development and Training	44

CHAPTER SEVEN	46

CONCLUSIONS AND RECOMMENDATIONS	46

7.1 Introduction	46

7.2 Conclusions	46

7.3 Recommendations	47

# LIST OF TABLES

Table 1:  Tanganyika District Council- Project Coverage Villages	1

Table 2: Land categories in Tanganyika District	9

Table 3: Mitigation Measures of Identified Impacts	22

Table 4: Social and Environmental Monitoring Plan	28

Table 5: Training conducted to Tanganyika E&S Team	34

# LIST OF FIGURES

Figure 1: Administrative Map of Tanganyika showing 16 Wards	6

Figure 2: Land categories in Tanganyika 	10

Figure 3: Map of Wildlife Corridor in Tanganyika District	11

# LIST OF ABBREVIATIONS AND ACRONYMS

| CBO | - | Community Based Organization |
| --- | --- | --- |
| CCRO | - | Certificate of Customary Right of Occupancy |
| CoC | - | Code of Conduct |
| CRO |  | Certificate of Right of Occupancy |
| DED |  | District Executive Director |
| DEMO | - | District Environmental Management Officer |
| DLHT | - | District Land and Housing Tribunal |
| E&S | - | Environmental and Social |
| EA | - | Environmental Assessment |
| EIA | - | Environmental Impact Assessment |
| EIAR | - | Environmental Impact Assessment Report |
| EIS | - | Environmental Impact Statement |
| EHSG |  | Environmental Health and Safety Guidelines |
| EMA | - | Environmental Management Act 2004 |
| EMO | - | Environmental Management Officer |
| ES | - | Environmental Screening |
| ESCP | - | Environmental and Social Commitment Plan |
| ESMT | - | Environmental and Social Management Team |
| ESMF | - | Environmental and Social Management Framework |
| ESMP | - | Environmental and Social Management Plan |
| ESF |  | Environmental and Social Framework |
| ESS | - | Environmental and Social Standard |
| FPIC | - | Free, Prior and Informed Consent |
| GDP | - | Gross Domestic Product |
| GBV | - | Gender Based Violence |
| GoT | - | Government of Tanzania |
| GRM | - | Grievance Redress Mechanism |
| HIV/AIDS | - | Human Immunodeficiency Virus/Acquired Immune- Deficiency Syndrome |
| ILMIS | - | Integrated Land Management Information System |
| LGAs | - | Local Government Authorities |
| LTAP | - | Land Tenure Assistance Project |
| LTIP | - | Land Tenure Improvement Project |
| LTSP | - | Land Tenure Support Project |
| M&E | - | Monitoring and Evaluation |
| MLHHSD | - | Ministry of Land, Housing and Human Settlement Development |
| NEMC | - | National Environment Management Council |
| NGO | - | Non-Governmental Organisation |
| NSC | - | National Steering Committee |
| OHS | - | Occupational Health and Safety |
| OM | - | Operational Manual |
| PCU | - | Project Coordinating Unit |
| PLUM | - | Participatory Land Use Management |
| PO-RALG | - | President’s Office Regional Administration and Local Government |
| Rl | - | Residential License |
| RPF | - | Resettlement Policy Framework |
| SEA | - | Sexual Exploitation and Abuse |
| SEP |  | Stakeholder Engagement Plan |
| TNA | - | Training Needs Assessment |
| TOR | - | Terms of Reference |
| URT | - | United Republic of Tanzania |
| VEO |  | Village Executive Officer |
| VLUM | - | Village Land Use Management (Committee) |
| VLUP | - | Village Land Use Plan |
| VG | - | Vulnerable Groups |
| VGPF | - | Vulnerable Groups Planning Framework |
| WB | - | World Bank |
| WEO | - | Ward Executive Officer |

# CHAPTER ONE

# INTRODUCTION

## 1.0 Background Information

The Government of Tanzania (GoT) through the Ministry for Lands, Housing and Human Settlements Development (MLHHSD) is implementing Land Tenure Improvement Project (LTIP). The Project Development Objectives (PDO) are to strengthen the national land administration system and increase tenure security in selected areas for both men and women. LTIP promotes land-based investments and ensures inclusion for social economic development in both urban and rural areas. Key project results indicators related to the PDO to increase tenure security include the registration of 1 million Certificates of Rights of Occupancy (CROs), one million Residential Licenses (RL), and 500,000 Certificates of Customary Rights of Occupancy (CCROs). At least 40 percent of the land certificates should be registered under the name of women, as sole owners, or co-owners. Project investments are also expected to support a reduction of at least 30 percent in the number of land conflicts, as well as an increase in perception of tenure security. Results indicators related to the PDO to  strengthen the national land administration system include an increase of 20 percent in the number of CRO transactions, a reduction of the average time to issue CROs (first registration) from 180 days to 60 days.

## 1.1 LTIP Project Scope in Tanganyika District Council

The Tanganyika District Council is one of beneficiaries of LTIP activities. In Tanganyika the project is expected to support the preparation of Village Land Use Plans (VLUP) and Detail Settlement Plan (DSP) covering the settlement part of the villages, as well as the issuance of CCROs, renovation/creation of district and village land offices. This ESMP is prepared specifically to guide the preparation of VLUP, DSP, and issuance of CCROs activities covering all 23 villages (see table 1) while the ESMPs for district and village land offices will be developed later before commencement of the renovation activities.

##### Table 1:  Tanganyika District Council- Project Coverage Villages

| NO. | Ward | Village | Registration Date | Village Registration Number |
| --- | --- | --- | --- | --- |
| 1 | Kapalamsenga | Kapalamsenga | 1987 | RK/KIJ/2 |
| 2 | Kapalamsenga | Songambele | 01.09.2012 | RK/KIJ/96 |
| 3 | Kapalamsenga | Itunya | 01.09.2012 | KT/KIJ/40 |
| 4 | Ikola | Kafisha | 01.09.2012 | KT/KIJ/42 |
| 5 | Isengule | Isengule | 1975 | KT/KIJ/247 |
| 6 | Isengule | Shukula | 2014 | 74 TDC |
| 7 | Isengule | Kasangantongwe | 01.09.2012 | KT/KIJ/41 |
| 8 | Kasekese | Kagunga | 2014 | 62 MDC |
| 9 | Katuma | Kapanga | 01.09.2012 | KT/KIJ/43 |
| 10 | Katuma | Kamilala | 2014 | 65 MDC |
| 11 | Katuma | Mpembe | 1962 | RK/VC/29 |
| 12 | Mwese | Lugonesi | 1975 | RK/VC/251 |
| 13 | Mwese | Lwega | 1979 | RK/VC/249 |
| 14 | Mwese | Bujombe | 2014 | 58 MDC |
| 15 | Tongwe | Ngomalusambo | 1993 | RK/KIJ/372 |
| 16 | Tongwe | Bugwe | 01.09.2012 | RK/KIJ/374 |
| 17 | Mpanda ndogo | Igagala | 01.09.2012 | KT/KIJ/53 |
| 18 | Mpanda ndogo | Mchakamchaka | 1974 | RK/KIJ/21 |
| 19 | Mpanda ndogo | Igalula | 1979 | RK/KIJ/284 |
| 20 | Mpanda ndogo | Katobo | 01.09.2012 | KT/KIJ/52 |
| 21 | Kabungu | Kasinde | 01.09.2012 | KT/KIJ/48 |
| 22 | Mnyagala | Kamsanga | 01.09.2012 | KT/KIJ/50 |
| 23 | Mnyagala | Ikaka | 2014 | 67 MDC |

In Tanganyika District Council, the preparation of VLUP, DSP and the issuance of CCROs is expected to involve the following activities:

- Village Land Use Plans (VLUP) and

There are 55 villages formally registered in Tanganyika district, of which already 26 already have VLUP. LTIP is expected to support the preparation of VLUP (review VLUP in six villages and preparation of VLUP in 4 villages) and DSPs for the 23 villages reached by LTIP in the district, as this is a prerequisite for the issuance of CCROs. The preparation of VLUPs will involve awareness creation and capacity building for the Participatory Land Use Management Team (PLUM); conduct village assembly and formulation of Village Land Use Management Council (VLUM); preparation of baseline information which include resource assessment, existing land use and existing environmental and social issues; preparation of draft Village Land Use Plan (VLUP); validation and approval of the proposed VLUP and respective by-laws by the village assembly; endorsement of the VLUP by the district council; gazettement of the approved VLUP by the National Land Use Planning Commission. For each VLUP and DSP, LTIP will support an adequate assessment of E&S implication and the formulation of advice for addressing these in ways that are consistent with the World Bank’s ESF.

- Issuance of CCROs

The process of issuance of CCROs is detailed in the LTIP CCRO Manual and shall involve five (5) major activities namely:

- Public awareness and engagement of marginalized groups (people with disabilities and old people);

- Employing and Training of Para- surveyors;

- Parcels adjudication;

- Preparation of DSP (regularization layout);

- Block Planning and Negotiation of Road Accessibility

- Printing and issuing CCROs.

The aforementioned activities involved in the issuance of CCRO have potential to cause environmental and social (E&S) risks and impacts. To address the potential E&S risks and impacts the Project has prepared this Environmental and Social Management Plan (ESMP) for Tanganyika District Council.

## 1.3 General Objectives of ESMP

The preparation of the Tanganyika VLUPs, DSPs and issuance of CCRO have potential to cause E&S impacts. The Tanganyika ESMP is a tool for identifying, mitigate, and monitoring the E&S impacts associated with these activities. Specifically, it depicts how the organizational capacity and resources will be utilized to assess these impacts, define mitigation measures, and implement them when appropriate. Therefore, the Government’s implementation team, as well as Non-Governmental Organizations (NGOs) that are expected to be hired under LTIP to support rural land certification, will implement project activities in accordance with this ESMP.

The preparation of this ESMP is consistent with the Project’s Environmental and Social Management Framework (ESMF) and aims at attaining the following objectives:

Identify potential E&S risks and impacts associated with land use planning and rural certification activities support by LTIP;

Develop mitigation/enhancement measures to minimize E&S risks and impacts;

Define implementation arrangement and organization structure of ESMP implementation including assessment of the implementation capacity of the implementing agencies (LGA)

Identify the parameters to be monitored and the respective tools that are used in monitoring and reporting.

## Methodology for Preparation of ESMP

This ESMP has been prepared by the district Participatory Land Use Management Team (PLUM) of Tanganyika District Council in collaboration with the LTIP-ESMT through the following activities.

- Undertake an E&S screening to determine risks and impacts associated with certification process using: (i) Annex 4 of ESMF on Screening Checklists for environmental and social issues; (ii) Annex 6: Environmental and Social Safeguards Criteria for selecting project specific areas; and (iii) Annex 5: Terms of Reference for the preparation of ESMP. Annex 1 for this ESMP on villages with existing VLUP

- Define mitigation, enhancement and monitoring measures for the identified impacts;

- Validation of mitigation, enhancement and monitoring measures through stakeholders’ engagement.

- Finalization of ESMP report, and sharing with wider stakeholders, including ESMP publication on the LTIP website.

# CHAPTER TWO

# BASELINE ADMINISTRATIVE, ENVIRONMENTAL AND SOCIAL CONDITION OF THE PROJECT AREA

  - Introduction

The baseline environmental and social conditions of Tanganyika district describe biophysical and social issues which are likely to be affected, trigger conflicts or are of biological importance in the district. The biophysical and social issues in Tanganyika necessitates for the project to ensure that mitigation measures are put in place to avoid risks and impacts to the communities. The main and indigenous ethnic group in Tanganyika is Bende. They constitute almost 60 percent of the entire ethnic group’s population in the district. Other ethnic groups are Sukuma, Fipa, Waha, Hutu, Tongwe and Nyakarema. Religious groups available in Tanganyika are mainly Christians, Muslims and few adhere to traditional beliefs. The main food stuff is ugali derived from maize or cassava flour and rice. The dominant economic activities in the district are agriculture being practices by majority of the community as well as livestock keepers. Other economic activities are trade, fishing and mining.

  - Administrative Condition of Tanganyika District Council

Tanganyika District is one of the three Districts in Katavi Region namely Mpanda District and Mlele district, Tanganyika district lies between latitudes 50 15 to 70 03’ south of Equator and longitude 300 to 330 31 East of Greenwich. Tanganyika district was established on 1st July, 2016 by GN number 69 of 29.01.2016 after the division of the ancient Mpanda District.

Administratively, Tanganyika District is divided into three divisions which are Kabungu, Mwese and Karema and 16 Wards (Figure 1), 55 Villages and 328 hamlets. The District Council has a total of 22 Councilors of which 16 of them are elected and 6 are appointed to special seats. The district has one electoral Constituency and one Member of Parliament.

#### Figure 1: Administrative Map of Tanganyika showing 16 Wards

2.3 Environmental Baseline Information in Tanganyika District Council

Terrain of Tanganyika District: The topography of Tanganyika district is divided into five topographical features, these includes:  Ranges of mountainous highlands, Gentle undulating upland with hills, Valleys, Lowland and  steep hills, gentle plateau and plains, Karema depression with very gentle plain. The district is generally dominated by Mwese highlands in the western part of the district.

The mountainous areas:

This is the continuation of the Southwestern highlands that form the undulating topography with range of mountains ranging from 1400 to 1900 meters above sea level. This covers the northern and Northeastern part of Mishamo extending to the boundary of Uvinza district; the Mwese Lugonesi ridge which extends to the southeast to Kasegese and Kaseganyama which are located at the foots of the ridge; also, the high lands located at the western side of Bugwe.

The Mid gentle Undulating Upland

These are areas with height ranging from 1,000 to 1,300 meters above sea level. This covers the whole of Mishamo wards, the western part starting from the ending edge of Karema depression to the foots of the range of Wansisi hills; areas of Nkamba forest reserve, Katavi National Park, and areas lying at the eastern part from Sibwesa, Kapanga, Bugwe to the southeastern part of Tongwe East Forest Reserve.

The low land zones:

This is found along the lake shore extending widely inland from Karema, Ikola Isengule and Kapalamsenga wards having a range of latitude from 700 to 1,000 above sea level. The Karema depressions experience warm and  dry weather conditions with moderate rainfall supporting rice growing.

Valleys:

The major valley starts from Katuma village, Katuma river with water shed that drains its water into Lake Rukwa through Katavi National Park; while at the other side there is another river which drains water into Lake Tanganyika at Rukoma crossing Lubalisi, Ikubulu in Uvinza District, it is also used by migratory animals from Katavi National Park to Mahale and vice versa. The northern valley which starts between Kilando and Sunuka at Lake Tanganyika in Uvinza crossing the Mishamo settlement through Mlabansi, Ifumbula, Bulamata to the eastern side following Mnyamasi tributaries to Ugalla River, Generally, these are the fault fragments of the western leg of great lift valley extending outwards from Lake Tanganyika.

Lake Tanganyika

This is among of the deepest lakes in the world. Lake Tanganyika forms western leg of the Great Rift Valley. Tanganyika District covers 161,874 Km square of Lake Tanganyika water body.

Other main water bodies in Tanganyika District include Rugufu River which starts from Bugwe Mountains, passes through Mishamo camp and join Mnyamasi River. Mnyamasi River starts from Mpembe village in Katuma ward join Ugalla river through Tongwe East Forest Reserve and pours water into Malagarasi River which finally drains into Lake Tanganyika. Lwegere River starts from Tongwe west forest reserve passes through Lugonesi and join Lwega River and finally pours water into Lake Tanganyika.

Districts and other areas bordering Tanganyika District: The Tanganyika district is bordered with Mpanda Municipal, Nsimbo Council, Nkasi District, Kaliua District, and Uvinza District. Presence of Lake Tanganyika, wildlife corridors to Mahale Mountains and Katavi National Park, grazing land and bordering with multiple district councils necessitates the need for the LTIP to recognize mixed land uses and engagement of several stakeholders.

Major Land Use in Tanganyika District:

Agricultural:

It is estimated that about 85 percent of the population in the district depends on agriculture and livestock keeping for their livelihood. Total District arable land is 393,400 Ha but only small portion of arable land is being cultivated (79,288Ha is cultivated). It is anticipated that if modern crop; production and improve animal husbandry is applied; the district could increase production of both food and cash crops tremendously. The main food crops are Maize, Cassava, Millets, Paddy, Beans, Sweet Potatoes, Potatoes, Finger Millet, Bananas and Vegetables/Fruits. Cash crops are Tobacco, Groundnuts, Sunflowers, Simsim, Coffee, Palm Oil; with recently Cotton and Cashew.

Agro-Ecological zones:

Tanganyika district is classified into four Agro- economic zones namely: Mwese Highlands, Karema Depression, Kabungu Plateau and Lake Tanganyika shore. The following table shows a summary indicating locality, altitude, climate, soil and the main economic activities for respective zone in the district.

Table 2: Classification of Agro-Ecological zones in Tanganyika District Council

| Zone | Location | Altitude | Soil and Rainfall | Main Economic Activities |
| --- | --- | --- | --- | --- |
| Mwese Highlands | Mwese Division | Altitude 1100-2500m | Soil- sandy clay loam with good drainage main soil order ultisol (Hilly) Rainfall- 10-1100mm | Agriculture Maize, cassava, beans, bananas, coffee, Irish potatoes Livestock Cattle, sheep, goats, poultry, Others, beekeeping |
| Karema Depression | Karema Division | 1000-1300m | Soil- sandy clay loam Ferrosols Rainfall- Annual Rainfall averages is about 1200mm. | Agriculture Maize, cassava, paddy, Sunflower Livestock Cattle, goats, sheep, poultry Others Fishing & Lumbering |
| Katumba plain | Kabungu Division | 1000-14000m | Soil- Sandy loam with good drainage. Rainfall is ranges 1000-1300mm | Agriculture Maize, Cassava, paddy Sunflower, cotton, Cashewnuts, Livestock Cattle, goats, sheep, poultry Others Beekeeping |
| Lake Tanganyika | Karema Division | 770-1300m | Soil- sandy loam with good drainage. Main soil Vertisol Rainfall 950-1200mm | Agriculture Maize, cassava, Palm oil, paddy Livestock Cattle, goats Others Fishing |

Source; Tanganyika district Council, 2023

Reserved Land

Reserved land is defined under Land Act no. 4 of 1999 to mean land reserved, designated, or set aside under the provisions of, Forest Act, National Parks Act, the Marine Parks and Reserves Act, Wildlife Conservation Act.

Reserved areas in Tanganyika District include village forest reserves, Tongwe East and West District forest reserves, Nkamba forest reserve Mpanda North forest reserve (managed by TFS), Wildlife corridor and Katavi National Park. These areas are endowed with abundant natural resources.

##### Table 2: Land categories in Tanganyika District

| No. | Land Category | Ha | Percent |
| --- | --- | --- | --- |
| 1 | General land | 47,606 | 2.8 |
| 2 | Reserved land /forestry | 732,402 | 43.4 |
| 3 | Water bodies | 161,874 | 9.6 |
| 4 | Village land | 745,018 | 44.2 |
|  | TOTAL | 1,686,900 | 100 |

Source; Tanganyika district Council, 2023

In Tanganyika district, only 684km2 of land is outside the Game Controlled Area. The prevailing land categories is detailed in Figure 2.

#### Figure 2: Land categories in Tanganyika (Source: Tanganyika District Council Land Use Framework Profile, 2018).

Conservation Areas: The district plays an important role in conservation of major ecosystems including forest reserves 593,709 Ha, Katavi National Park 73,416 Ha and Wildlife Management Area (WMA) 65,277Ha. These areas make important ecosystem with high biological and conservation value, an important aspect to be noted for consideration by the LTIP project.

Wildlife Corridors: In the district there is a wildlife corridor which will require recognition by the LTIP during undertaking of the preparation of VLUPs, and rural certification activities. The corridor found in Tanganyika district is Lyamgoloka wildlife corridor which links Katavi national park and Mahale national park.

#### Figure 3: Map of Wildlife Corridor in Tanganyika District

Land certification process, National parks, and other land uses: The proposed rural certification will be implemented in a way that is consistent with the safeguards requirements as stipulated in LTIP ESMF, which provides screening criteria to check for environmental and social issues on villages before developing the ESMP for the entire Tanganyika District Council. Based on Annex 6 of the LTIP ESMF, conservation areas will be recognized as such and no CCROs will be issued in these areas. Annex 6 of the ESMF further stipulates that in the event where boundaries between the reserve land, national park and individual land parcels are not agreed, LTIP will not proceed with the issuance of CCROs until boundary related conflicts are resolved.

## 2.4 Tanganyika District Council Social Baseline Information

People and Population: According to the 2022 Population and Housing Census Tanganyika District Council has a population of 371,836 people (184,842 Males and 186,994 Females) and 68,279 households.

Project Workforce Requirements: VLUPs and the rural land certification process in Tanganyika District Council will require workforce. This situation is likely to attract influx of people in search of employment from within and from outside the district. The presence of internal and external movement of people necessitates for the LTIP to pay attention on labor management and eligibility for land rights during issuance of CCRO.

Economic Activities: The Tanganyika district economic structure is based on agriculture, livestock keeping, trade, beekeeping, and mining as the source of livelihood for the majority of residents. The district is also endowed with wildlife resources which plays the major role in socioeconomic development of the district through ecological, aesthetic, spiritual, and research values.

Social Services: Tanganyika district council has primary and secondary schools, health centers, churches, mosques and market which are located in all 16 wards, owned by the government, private sector and religious institution. Provision of land parcels for social services such schools, health centers, churches, mosques and markets is critical for the LTIP and necessitate the project to ensure that these facilities are identified and provided with the CCRO to improve their tenure security. The large section has electricity supplied by TANESCO. The main source of drinking water includes boreholes and river streams.

Road Infrastructure: The district has poor road infrastructure that limit transportation services especially during rainy season. There is one National Tarmac Road which passes along Katavi – Kigoma with coverage of 30 km and three (3) Regional roads covering 310 km at gravel level. The gravel road connects the district of Uvinza, Mishamo settlemets and Lake Tanganyika. Other road networks in the district are under management of TARURA with total length of 1,029.9 connects wards to the entire district. This situation will prevent access to and individual plots. LTIP will take note of lack of access roads especially in rural side of the district and ensure that all land parcels including grazing areas and wildlife corridors are identified and provided with access. Indeed, LTIP Team will be required to properly plan transportation for effective implementation of certification of CCROs activities.

Conflicts over Land resources: The district also experiences conflicts with conservation authorities over land as the district plays an important role in conservation of major ecosystems in the district.  LTIP is required to recognize relevant conservation authorities to avoid conflicts between government ministries and conservation authorities. In particular, LTIP Team are required to closely observe ESS7, ESS6 and ESS10 requirements and provisions during VLUPs and rural land certification activities.

A multitude of NGOs and CSOs operate in Katavi Region and Tanganyika District: There are 43 NGOs/CSOs actively working in Katavi region with different objectives and missions. Their areas of involvement, among others, are tourism, conservation of environment and natural resources governance, good governance and human rights, gender and youth empowerment, socio-economic development and empowerment, climate change and securing land tenure.  In some cases, the activities of these organizations conflict with one another. While CBOs, NGOs and CSOs can help LTIP to meet its objectives, they can also confuse the communities, especially if they provide them with incorrect and or distorted information about the project. LTIP is supposed to recognize this risk and strategize the engagement of NGOs/CSOs that work in Katavi and Tanganyika districts. In particular, deliberate efforts to map and understand and subsequently provide them with relevant information about the project are necessary. This will help to make them not confuse LTIP with other land-related projects which have been implemented within their localities.

GBV/SEA and Diseases Transmission: Like other areas in Tanzania, HIVI/AIDs is prevalent in Tanganyika District. Proposed project activities including the preparation of PLUM, VLUP and issuance of CCROs will increase interactions between project workers and local community which is likely to trigger social issues such as GBV/SEA and spread of HIV/AID. In order to avoid GBV/SEA, spread of HIV and AIDS as well as conflicts between project workers and the community the project will require all workers to sign code of conduct (CoC).

# CHAPTER THREE

# LEGAL AND INSTITUTIONAL FRAMEWORK

## 3.1 Introduction

This chapter describe relevant legal and institutional framework governing the preparation of VLUP, DSPs and issuance of CCRO in Tanganyika district. The focus has been made on legislations which provide environmental and social provisions and requirements relevant for the Project. The legislation described in this chapters are those which provide guidance to the project and can be made actionable to assist the project on the management of E&S risks and impacts.

## 3.2 Country’s Legal Framework to Guide Land Use Planning and Rural Certification Processes in Tanganyika District

The Wildlife Conservation Act No. 5 of 2009: The Act provides measures for the general conservation of wild animals which includes declaration of wildlife protected areas, game reserves, wetlands and game-controlled area to mention a few. This Act will be implemented by the project through the use of Annex 6 of the LTIP ESMF. Wildlife Conservation Act is the main legal provision for the establishment of the existing wildlife and wetland protected area and is also the basis for the prevention of any encroachment with the project activities. Tanganyika is endowed with the significant areas for wildlife and national parks which calls for the project to ensure that these areas are identified through guidance provided by Annex 6 and that no certification will be conducted in national parks.

The Environmental Management Act (EMA) 2004: The Act provide guidance for regulation process in sensitive areas such as rivers, lakes, wetlands, forest areas, and wildlife resource among others. The Act provides a legal framework for coordinating harmonious and conflicting activities by integrating those activities into overall sustainable environmental management system by providing key technical support to Sectoral Ministries. The EMA will be applicable by the LTIP team in Tanganyika during identification of national parks and preparation of DLUPF and VLUP. Specifically, LTIP project in Tanganyika District Council will adhere to 60m buffer zone requirements when issuing CROs for land parcel near lake Natron.

The National Land Act, No. 4 and 5 of 1999: The Land Act (1999 recognize that all land in Tanzania belongs to the public, and the President acts as the trustee of the land for the benefit of the people (Land Act, § 1(1)(a)). The Land Act classifies all land in Tanzania into three categories: (1) Reserved Land, (2) General Land, and (3) Village Land (§ 4(4)). The first two categories are governed under the provisions of the Land Act and its regulations. About 68% of all land is Village Land; 30% is Reserved Land and only 2% is General Land in the Country.

These Acts among other things outlines, procedure for land administration, allocation, acquisition, schemes of regularization, land registration and certification, compensation and resource management in both urban and rural areas. The Land Acts contain provisions of critical environmental importance and modalities for stakeholders’ engagement through meeting and public hearing. Both Acts translates the fundamental principles of land policy into the body of the law. One of these fundamental principles is to ensure that land is used productively and that any such use complies with the principles of sustainable development. The preparation of  VLUP and the issuance of CCRO will be conducted in accordance with the provisions and requirement stipulated in Land Act. Section 32 (1) and section 33 of the land use planning Act No. 6 of 2007 provides directives and requirements for the preparation of both DLUFP and VLUPs.

The land use planning Act, 2007: LTIP shall prepare the VLUP in accordance to this Act, the act provides that the village must have defined boundaries and gazetted under the GN and described in Village Certificate issued by Commissioner of Land; This act is making reference to other acts especially the Land Act No 4 and 5 to guide the entire process of Land use planning practice in Tanzania.

The Occupational Health and Safety Act, No. 5 of 2003: The law requires employers to provide a good working environment to workers in order to safeguard their health. The LTIP will ensure the implementation of this Act through training to drivers to eradicate incidences and accidents, provide appropriate Personal Protective Equipment (PPE) and welfare facilities such as tents, drinking water and toilet to the direct and indirect implementing teams during preparation of DLUPF, VLUP and the issuance of CCRO.

The Employment and Labour Relations Act, No. 6 of 2004: The Act provide labour rights and protections particularly on Child labour, forced labour and discrimination in the working place and freedom of association. The act prohibits child labour it provides that no child under the age of 14 shall be employed. LTIP will ensure equality in employment, forbid child labour and provide valid employment contracts to direct and indirect workers. The employment contracts for direct and indirect teams will ensure compliance to basic employment standards which include: i) Wage determination that stipulates a minimum term and condition of employment (ii)  An employment standard constitutes a term of a contract with an employee unless -a term of the contract contains a term that is more favorable to the employee; and  a provision of an agreement alters the employment standard to the extent permitted by the provisions and iii) a provision of any collective agreement, a written law regulating employment, wage determination or exemption granted under section 100. The law also requires provision for health insurance and joining to National compensation funds for labour on employment beyond six months.

The Urban Planning Act of 2007: This is the principal legislation which govern urban planning.  The LTIP will prepare detailed planning schemes; undertake public and other stakeholder’s engagement; and subsequent facilitate approval of scheme of regularization as stipulated in this Act. The project will also spearhead preparation of environmental and social assessment of the proposed scheme of regularization.

Public Health Act of 2012:  The act stipulates need to consolidate public health through prevention of disease, promotion, safeguard, maintain and protect the health of humans and animals. The presence of LTIP workers may result in the risk of disease transmission and will be addressed through conducting HIV/Aids campaign, provision of handwashing facilities, condoms and dustbins.

Water Resources Management Act No. 11 of 2009:  Water Resource Management Act No. 11 of 2009 is the principal legislation governing the utilization and pollution control of the water resources. Specifically, the objective of this Act is to ensure that, water resources are protected, used, developed, conserved, managed and controlled for sustainable development. The LTIP will identify boundaries of Lake Natron, streams, rivers and other water sources in Tanganyika District Council and ensure that such uses are included during preparation of DLUPF and VLUP and will not issue CCRO in such areas to enhance management of water resources.

The Agriculture and Livestock Policy of 1997:  Main objective is to promote and ensure a secure land tenure system to encourage optimal use of land resources and facilitate broad-based social and economic development without upsetting or endangering the ecological balance of the environment. The LTIP implementation in Tanganyika will have adhere to this policy so as to protect the rights of hunters, gatherers, livestock keepers, and specific use endowed to the VGs.

## 3.3 World Bank Environmental and Social Framework

Project ESMF has identified ESS1, ESS2, ESS3, ESS4, ESS5, ESS6, ESS7, ESS8, and ESS10 to be applicable to the LTIP. However, for Tanganyika District Council the following ESSs are applicable and this ESMP describe how specific ESSs is operationalized during preparation of DLUPF, VLUM and the issuance of CCROs:

ESS1 Assessment and Management of Environmental and Social Risks and Impacts:

- Screening and of environmental and social risks and impacts, to determine level and magnitude of risks and impacts.

- Prepared ESMP for Tanganyika for mitigating identified risk and impacts; monitoring effectiveness of proposed mitigation measures as well as enhancing project benefits.

ESS2 Labor and Working Conditions;

Provision of Valid Employment Contractors to workers for both direct and indirect teams;

Provide PPE and welfare facilities to workers;

Training HIV/Aids to project workers of direct and indirect team;

Provision of occupational and safety awareness and services to workers

ESS4 Community Health and Safety

Sensitization of community about the project and associated health risks and impacts; and

Training on HIV/Aids to project workers of direct and indirect team;

Training on community and road safety

Awareness on accident risks and community safety.

ESS5 Land acquisition, Restriction on Land use and Involuntary Resettlement

- Sensitization of community about the project and land requirements for access roads, community facilities such as schools, health facilities, markets, cemetery; reactional and open areas; and

- Land donation/acquisition requirements and procedures as stipulated in Resettlement Policy Framework (RPF);

ESS6 Biodiversity Conservation and Sustainable Management of Living Natural Resources

- Use of Annex 6 to ensure that no certification will be undertaken in reserved or conservation land or ecological resources of biodiversity importance such as Lake Natron

- Identification of boundaries of national parks, reserve land, water bodies and wildlife corridors in areas without conflicts with the grazing land.

ESS10 Stakeholders Engagement and Information Disclosure

- Sensitization of community about the project

- Formulation and operationalization of Grievance Redress Mechanism (GRM)

- Implementation of District Stakeholders Engagement Forum (DSEF) and National Stakeholders Engagement Forum (NSEF).

# CHAPTER FOUR

# ENVIRONMENTAL AND SOCIAL IMPACTS, RISKS AND MITIGATION MEASURES

## 4.1 Introduction

Based on environment and social (E&S) baseline condition of the project area, the E&S assessment has identified the following likely project benefits, risks and impacts:

## 4.2 Project Social Benefits

In Tanganyika District the LTIP will create the following benefits:

Security of Tenure: Issuance of CCROs will enhance security of tenure to the individual, community member and institutions. For instance, issuance of CCROs to the group of people owning jointly grazing lands will protect such resources from individual encroachment and appropriation.

Capital Creation: Individuals and communities has potential to use CCROs as collateral to access capital from financial institutions because have legal representation. This will help to accumulate capital which will be invested in other productive economic activities which will stimulate development within Tanganyika district.

Reduction of Cost Associated with Informal Land Transaction: The provision of CCROs to Tanganyika communities will enhance reliability in land transaction. CCROs serve as evidence of ownership of land with clear size and boundaries. Equally, it will discourage the practice of multiple sales of the same land to different buyers thus reducing land related conflicts.

Employments Opportunities: Rural certification activities in Tanganyika district will require workforce to perform different activities. In total the project will employ approximately over 50 People both skilled and unskilled.

## 4.3 Negative Social Risks and Impacts of Land Use Planning and Rural Land Certification

The following are major negative social impacts associated with LTIP regularization activities in Tanganyika District Council.

- VLUP:  LTIP project will ensure that the villages have no contradicting GN before preparation of VLUP failure to do so is likely to disrupt to ecology of the wildlife. Some decisions made as part of the VLUP preparation may also have E&S impacts. These will be assessed, and mitigation measures will be proposed as part of the VLUP preparation process.

- Crosscutting Impacts due to Land use planning and rural land certification

Conflict over land ownership and rights: In project areas people are living without proper identification of their areas, land size and boundaries with neighbors. During adjudication process the chances of not agreeing to the boundaries might lead to conflict over land use and the conservation authorities. In addition, some conflicts might involve proving evidence on who are legal owner of the land parcels to be issued with CCROs. Such cases are likely to happen especially in bouldering land parcels, extended and polygamous families, inherited land parcels and on land parcels which people have contested interest and ownership rights.

Similarly, individuals and communities residing close or who have encroached conservation areas might require CCROs on such land thus leading to conflict with authorities.

Ineligibility to CCROs: According to the Annex 6 of ESMF and CCRO’s Manual guiding certification process, communities residing within road reserve, protected area and other sensitive areas are not eligible for CCROs. Such areas are reserve lands and are restricted from human settlements and other social economic activities. Considering that land use restriction may be defined or formalized as part of the VLUP process (e.g., establishment of village forest reserves and/or village grazing land), there is a possibility that some individuals using these areas may lose access rights and/or may find out that they are ineligible for CCROs.  Community members falling under such circumstances might consider having been denied project benefits related to CCROs. Some may also question the criteria used to establish land use restrictions as part of the VLUP process.

Inequalities for Women and other Marginalized Group: Marginalized groups such as elders, chronically ill people and the youth have less chances to get CCROs due lack of project information, and this could formalize inequalities between men and women regarding access to CCROs.

Gender Based Violence, and SEA: In Tanganyika, community members with access to project resources such employment, income and power over others might subject subordinates, children, spouses, and people from low-income status to GBV and SEA.

Influx of Laborers: Mass rural certification will involve large number of workers from within and outside the project areas. Interactions of project workers among themselves and local community are likely to accelerate the spread of STI, crimes as well as over burdening of available social services.

Inaccessibility of Project Sites: Large section of Tanganyika district is served with gravel and dirty roads which limits transportation especially during rainy season. Land certification process is likely to delay during rainy seasons and the issue of health and safety due to accidents

Possibility of Issuing CCROs to Non-nationals: Tanganyika district is neighboring Democratic Republic of Congo (DRC) and Burundians’ Refugee settlements which its nationals have much interaction to Tanganyika community thus putting risk of issuing CCROs to non-citizens due to demand of land.

## Project Positive Environmental Impacts of Land Use Planning and Land Certification

The following are positive environmental impacts of this project in Tanganyika District Council:

Enhancement of protection of sensitive areas and minimization of Conflicts: Tanganyika district plays an important role in conservation. VLUPs and the issuance of CCROs will recognize all protected areas which will reduce their encroachment and conflicts between local community and conservation authorities.

Protection of Common resources: In Tanganyika district, group of people owning jointly grazing lands will be issued with CCROs. This will help to use the land sustainably and conserve and rangelands and water resources.

## 4.5 Negative Environmental Impacts of Land Use Planning and Land Certification

The major negative environmental impacts of regularization process in Tanganyika District Council are:

Encroachment of Sensitive Areas: Important conservation areas such as major ecosystems of Lyamgoloka wildlife corridor, Katavi National park, water source reserves and forest reserves requires to be protected. Inadequate and failure to recognize such areas during rural certification might lead to their encroachment.

Soil Erosion and Solid Waste Generation: Installation of the beacons may result in localized soil erosion due to the presence of loose soil around the beacon. Also, fabrication of beacons activities will involve sourcing materials from quarries and borrow pits such as gravel, sand, which may result in land degradation and soil erosion.  In addition, during certification process project workers will generate solid and liquid wastes such as plastic, food and human waste leading to land pollution such as oil spill during car maintenance.

Health and Safety Hazards: Fabrication, transportation and subsequent installation of beacons might lead to incidences and accidents causing injuries and fatalities to workers and community members.

## 4.6 Mitigation Measures of the Identified Impact

This section describes mitigation measures for the project adverse impacts and proposed measures for enhancing positive one as well as associated costs. Table 3 is the impacts and mitigation matrix for rural certification for Tanganyika District. It detailed the proposed impacts, mitigation measures, responsible party, timeframe and costs that will be overseen and managed by LTIP project implementation team.

##### Table 3: Mitigation Measures of Identified Impacts

| Sn | Potential Impacts | Mitigation Measures | Cost Estimates (TZS) | Responsible |  | Implementation Time Framework |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Implementation | Supervision |  |  |
| Negative Project Social Impacts |  |  |  |  |  |  |
| 1 | Negative economic and social impacts relating to restrictions on land use resulting from VLUP processes | - Undertake adequate E&S assessment of the proposed VLUP to determine the magnitude of impacts. - Devise mitigation measures to address risks and impacts related to the proposed VLUP in accordance with the World Bank’s ESF. | 1,000,000 | - Tanganyika District Council E&S Team - Ward and village leaders - CSOs | ESMT | During preparation of VLUP. |  |
| 2 | Deepening of insecurity on the fate of lands among Tanganyika communities. | - Provide communities with correct project information. - Strategize engagement of traditional leaders. - Ensure present and future village land use needs are taken into consideration during formulation of VLUPs without prejudice the need of other land uses and conservation of the environment. | 30,000,000 | - Participatory Land Use Management (PLUM) Team. - E&S Team - CSO | ESMT | During preparation of VLUP and issuance of CCROs |  |
| 3 | Confusion of communities with incorrect information about the project. | - Map NGOs/CSOs and understand their mission and objectives. - Provide NGOs/CSOs with project information and where necessary engage them to create sensitization to the community. | 5,000,000/= | - E&S Team - Participatory Land Use Management (PLUM) Team. - WEOs, CDOs and - VEOs - Traditional and religious leaders | ESMT | During preparation of VLUP & throughout the project. |  |
| 4 | Conflict over land ownership and rights | - Formulation and operationalization of GRM - Capacity building and awareness creation to local leaders on conflict resolution. - Sensitization on the importance of joint land titling. - Educate men on the importance of including their wives on CCROs. | 30,000,000/= | - Tanganyika District Council E&S Team - Ward Executive Officer (WEO), - Ward Community Development Officer (CDO) - Village Leaders | ESMT | During preparation of VLUP and issuance of CCROs. |  |
| 5 | Ineligibility to CCROs | - Identification of all households ineligible to receive CCROs and formulation of advice on how to address their situation. - Identification of households and parcels close and within conservation and sensitive areas. - Awareness on ineligibility for CCROs. - Liaise with NEMC, TANAPA, Ngorongoro Conservation Area, - Basin Authority for further guidance, and the Ministry of Natural Resources and Tourism for further guidance. - TANROADS and TARURA | 10,000,000/= | - Tanganyika District E&S Team - Participatory Land Use Management Team (PLUM) - National Environmental Management Council (NEMC) - TANROADS& - TARURA - Katavi National Park Conservation Area, - Water Basin Authority - Ministry of Natural Resources and Tourism for further guidance | ESMT | During identification of Parcels. |  |
| 6 | The CCRO issuance process formalize land access inequalities for Women and other Marginalized Group | - Identification of marginalized groups such as people with disabilities, women, elders, chronically ill persons and youth - Sensitization on importance of CCROs and other project benefits. | 10,000,000/= | - Tanganyika District E&S Team - Ward Executive Officer (WEO), - Ward Community Development Officer (CDO) - Village Leaders - CSOs. | ESMT | During Project Sensitization and identification |  |
| 7 | Gender Based Violence | - Engage Police Gender Desk to train Project staff on GBV/SEA. - All LTIP staff to sign a code of conduct which include GBV/SEA issues. - Develop and operationalize GBV Action Plan for the District. - Disseminate information about the GRM and encourage population to report misconducts - Engage relevant government agencies and/ or NGOs in the district who provide support to survivors on GBV and SEA such as assistance for medical care, psychosocial support, legal redress, safety, etc. where necessary. | 10,000,000/= | - Tanganyika District E&S Team - Ward Executive Officer (WEO), - Ward Community Development Officer (CDO) - Village Leaders | ESMT | Before placement of employees and during rural certification process. |  |
| 8 | Influx of Laborers | - Community awareness on STIs transmission and basic hygiene practice and crimes - Give employment priority to unskilled laborers from within project areas. - Provision of welfare facilities such as water, toilets and food vending to project workers. | 5,000,000/= | - Tanganyika District Council Certification Office (CUCO) - Tanganyika District E&S Team - Village Leaders - Private Companies involved in rural certification activities. | ESMT | During Urban Certification Process. |  |
| 9 | Inaccessibility of Project Sites | - Target implementation of rural certification of villages not accessible during rainy season during dry season. - Provide suitable transport facilities. |  | - Tanganyika District Rural Certification Office (DRCO): - Tanganyika District Council E&S Team - Participatory Land Use Management (PLUM) Team | ESMT | During Rural Certification Process |  |
| 10 | Possibility of Issuing CCROs to Non-nationals | - Make use of National IDs during issuance of CCROs - Rural formalization team to work closely with local leaders to confirm citizenship of Project beneficiaries. | 10,000,000/= | - Tanganyika District Council Urban Certification Office (CUCO - Tanganyika District E&S Team - Ward Executive Officer (WEO), - Ward Community Development Officer (CDO) - Village Leaders - Migration Teams |  | During Rural Certification Process |  |
| Total Cost |  |  | 120,000,000 |  |  |  |
| Negative Project Environmental Impacts |  |  |  |  |  |  |
| 1 | Negative environmental impacts relating to land use classification adjustments resulting from Review of the GN | - Undertake adequate E&S assessment of the proposed VLUP to determine the magnitude of impacts. - Devise mitigation measures to address risks and impacts related to the proposed VLUP in accordance with the World Bank’s ESF. | 5,000,000 | - PLUM - E&S Team | ESMT | During preparation of VLUP. |  |
| 2 | Encroachment of Environmental Sensitive Areas | - Make use of Annex 6 of the ESMF to ensure that boundaries between national parks, reserve and grazing land are made clear during preparation of DLUPF, VLUP and before issuance of CCRO issuance. | 5,000,000/= | - PLUM - E&S Team - National Environmental Management Council (NEMC) - TANROADS& - TARURA - TANAPA, - Lake Tanganyika and Lake Rukwa Water BasinAuthority | ESMT | Before placement of employees and during rural certification process. |  |
| 3 | Soil Erosion, oil spills and Solid Waste Generation | - Undertake tree and grass planting - Provision of dustbins in all project areas - Use of welfare facilities such as toilets and water - No refuse, waste oils should be discharged into drains or onto site grounds. | 5,000,000/= | - Tanganyika District Council E&S Team - Private Companies involved in certification activities. - Village Leaders | ESMT | During Rural Certification Process. |  |
| 4 | Health and Safety Hazards | - Provision of PPEs (Mask, Boots, Gloves and Helmet) to workers. - Implementing Institution (LGA/Private/CSO) must make due diligence on OHS risk management, including primary suppliers’ workers. - Training drivers of direct and indirect teams on road safety - Implementing agencies to enforce rules for drivers and passengers. - Provide Health and safety Training to project workers | 30,000,000/= | - Tanganyika District Council E&S Team - Private Companies involved in certification activities. - Village Leaders | ESMT | During Rural Certification Process. |  |

# CHAPTER FIVE

# Monitoring of Environmental and Social Impacts

## 5.1 Introduction

Monitoring establishes benchmarks which are used to assess the level of compliance with ESMP. Monitoring will involve the continuous or periodic review of mitigation activities to determine their effectiveness. The monitoring plan in this report specifies the institution arrangement for execution of ESMP. In particular, it clarifies type of monitoring, who will carry out monitoring and what other inputs such as training are necessary.

The objectives of Environmental and Social monitoring plan are:

- To monitor the effectiveness and implementation of ESMP during planning and CCROs issuance phases of proposed mitigation measures;

- To confirm compliance with environmental, social and safety legislation/regulations during certification as well as safeguards tools and instrument in pace;

- To control the risks and ecological/social impacts;

- To ensure best practices management as a commitment for continuous improvement in environmental and social performance;

- To provide environmental information to community/stakeholders;

- To provide early warning signals on potential environmental degradation for appropriate actions to be taken so as to prevent or minimize environmental consequences;

The Table 4 below summarizes monitoring plan for urban certification in Tanganyika District Council.

##### Table 4: Social and Environmental Monitoring Plan

| S/N | Environmental/ Social Impacts | Monitoring Parameters | Targets/Legal Standards | Monitoring Methods | Frequency /Duration | Host institution Supervising institutions | Monitoring Budget |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Land Use Planning |  |  |  |  |  |  |
|  | E&S impacts of land use planning | Compliance of the ESS 1-8 and ESS 10 | 100% | Reports on Implementation of ESMP | Quarterly | ESMT & PIT | 8,000,000/= |
|  | Enhancement of Social Benefits |  |  |  |  |  |  |
|  | Security of Tenure | No. of CCROs issued in each Village | 50,000 | ILMIS data | Quarterly | ESMT & PIT | 4,000,000/= |
|  | Capital Creation | No. of Beneficiaries using CCROs to secure capital. | 10 | Project report | Quarterly | ESMT & PIT | 1,000,000/= |
|  | Reduction of land conflicts | No. of land conflicts identified and resolved as part of the CCRO issuance process | 20 | Project report | Quarterly | ESMT & PIT | 1,000,000/= |
|  | Employments Opportunities | No. of people employed | 50 | Report | Quarterly | ESMT & PIT | 1,000,000/= |
| Enhancement of Environmental Benefits |  |  |  |  |  |  |  |
|  | Enhancement of protection of sensitive areas and minimization of Conflicts | Number of CCRO issued in sensitive areas | 0 | Report | Quarterly | ESMT & PIT | 1,000,000/= |
|  |  | Number and hectares or village land declared as forest reserve | 100 Ha | VLUP Reports | Six Months | ESMT & PIT | 1,000,000/= |
|  | Protection of Common resources | Presence of group of people owning jointly grazing lands issued with CCROs | 5 | Scheme of regularization & Reports | Annually | ESMT & PIT | 1,000,000/= |
| Social Negative Impacts |  |  |  |  |  |  |  |
|  | Enhanced communities understanding of LTIP activities | - Acceptance of the LTIP activities by the communities in the Tanganyika district - Participation of traditional leaders in LTIP activities. | 50,000 | Reports | Quarterly | ESMT & PIT | 1,000,000/= |
|  | Ineligibility to CCROs | No of parcels identified as ineligible for rural land certification | 10 | Report | Quarterly | ESMT & PIT | 500,000/= |
|  | Inequalities for Women and Other Marginalized Group | Tailored local information campaigns organized with the support of NGO-CSOs | 1000 | Report | Quarterly | ESMT & PIT | 1,000,000/= |
|  |  | No od Project staff trained on women land rights and how to encourage the registration of women’s land rights as part of the CCRO process | 100 | Report | Quarterly | ESMT & PIT | 1,000,000/= |
|  |  | Percentage of Women with CCROs. | 30% | Report | Quarterly | ESMT & PIT | 0 |
|  |  | Marginalized Group with CCROs. | 10% | ILMIS Report | Quarterly | ESMT & PIT | 1,000,000/= |
|  | Gender Based Violation | No. of GBV/SEA cases reported. | 0 | Report | Quarterly | ESMT & PIT | 500,000/= |
|  | Influx of Laborers | Percentage of laborers employed from within the project areas. | 40% | Report | Quarterly | ESMT & PIT | 500,000/= |
|  | Inaccessibility of Project Sites | No of Village identified as not accessible | 0 | Report | Quarterly | ESMT & PIT | 500,000/= |
| Total |  |  |  |  |  |  | 24,000,000/= |
| Environmental Negative Impacts |  |  |  |  |  |  |  |
|  | Waste Management | No. of dustbins provided in three Mitaas | 150 dustbins @ village 3 | Report and observation | Quarterly | ESMT & PIT | 15,000,000= |
|  | Health and Safety Hazards | No. of incidence and accidents reported. | 0 | Report | Quarterly | ESMT & PIT | 1,000,000/= |
|  | Greenhouse gas emissions | No. Service Conducted | Service at every 5000 Km | Maintenance Report | Quarterly | ESMT & PIT | 12,000,000/= |
|  | Monitoring of oil spills | No of drums (100 liters) distributed for collect dirty oil | 1 Drums in each LGA | Report | Quarterly | ESMT & PIT | 4,000,000/= |
| Total |  |  |  |  |  |  | 32,000,000/= |

# CHAPTER SIX

# INSTITUTIONAL ARRANGEMENTS FOR IMPLEMENTATION OF ESMP

## 6.1 Institutions

The implementation of ESMP will follow the plan stipulated in ESMF. For Tanganyika District Council, the following institutions shall be involved in the implementation of this ESMP

Tanganyika District Council Rural Certification Office: This will be responsible for daily certification activities which will involve support to Tanganyika District Council E&S Team.

Tanganyika District Council E&S Team: This will be responsible for implementation of the E&S activities including the proposed mitigation and enhancement measures with the support from DURCO.

District Land Use Plan Framework (DLUPF) Team: This will be responsible for identifying different uses within the district. In Tanganyika, unique land uses such as national parks, wildlife corridors, grazing land, Lake Natron and other uses will be identified and included in the DLUPF.

Participatory Land Use Management (PLUM) Team: This will be responsible for identification of households residing along road reserve, gullies and river streams.

National Environmental Management Council (NEMC), Western Zone: Will provide further guidance on households residing along, gullies and river streams.

Tanzania Rural and Urban Road Agency (TARURA) and Tanzania Road Agency (TANROADS), Katavi Region: Will provide further guidance on households residing along the roads including payment of compensation where applicable.

Ward and Village Leaders: These will be involved in conflict resolutions through operationalization of project GRM, identification of marginalized groups such as women, elders, chronically ill persons and youth, and sensitization on importance of CCROs, waste management, GBV/SEA matters, health and safety and other project related benefits.

Civil Society Organization (CSOs) and Non--Governmental Organization (NGOs): During mapping of the CSOs - NGOs in Tanganyika, the following were identified: JANE GOODALL INSTITUTE - JGI, The Nature Conservancy (TNC), Frankfurt Zoological Society (FZS) and SNV.   They will be responsible for ensuring engagement of marginalized and vulnerable people in this project. Sensitization on importance of CCROs and other project benefits, importance of joint titling and GBV/SEA matters. For those CSO-NGOs which shall be involved with  VLUPs, and CCRO , they will  be responsible for provision of PPEs (mask, boots, gloves and helmet) to workers; training drivers of direct and indirect teams on road safety; provide health and safety training to project workers; provision of dustbins in all project areas; provision of welfare facilities such as toilets and water; tree and grass planting; dust suppression.

## 6.2 Supervision and Monitoring Roles

Project Environment and Social Management Team (ESMT): shall be responsible for ensuring compliance with ESMPs. In particular, the team will conduct regular audits and prepare the reports that demonstrate the suggested ESMP are being implemented accordingly. The team will be required to submit monthly reports to MLHHSD. The MLHHSD through PCU then will be required to submit quarterly reports on ESMP implementation to the World Bank.

## 6.4 Capacity Development and Training

Capacity development training for LTIP is stipulated in ESMF. For Tanganyika District council the following training have been provided to E&S Team at LGAs levels to enhance their capacity during preparation of DLUPF (Table 5). Several awareness raising meetings were also conducted with different stakeholders during preparation of DLUPF.

##### Table 5: Training conducted to Tanganyika E&S Team

| S/N | Name of Training | Training Institution | Date |
| --- | --- | --- | --- |
|  | Environmental and Social Framework Training to LGAs E&S Teams | World Bank | 13th – 14th December 2022 |
|  | Workshop for Review of the ESMPs | ESMT | 3 March 2023 |

Other E&S trainings are planned for Tanganyika District Council to enhance their capacity to implement this ESMP will be as follow.

- Health and safety training to project drivers and field teams.

- Training on implementation of ESMP to private firms to be conducted prior to certification process;

- Training of code of conducts for GBV/SEA and ethics practice to ESMT and Tanganyika District Council E&S Team.

# CHAPTER SEVEN

# CONCLUSIONS AND RECOMMENDATIONS

## 7.1 Introduction

This ESMP is specifically for Tanganyika District Council LTIP activities. It proposes mitigation measures to minimize the adverse impacts, while enhancing the positive ones. The assessment and evaluation process of the proposed project activities indicates that the project will bring net social benefits within the project area. Negative implications of this project have been identified, and need to be mitigated, in order to make this project environmental and socially sound.

## 7.2 Conclusions

Given the importance of multiple land uses in Tanganyika, ESMP shall be an important tool for facilitation of stakeholders engagement and sensitization so as to affirm with proposed land uses, village boundaries and access to CCRO.

Furthermore, there is no identification of any VGs group as per VGPF guiding document hence VGP will not be prepared regardless the fact that there are few villages with a good number of pastoralist

The social benefits of this project to include enhanced security of tenure, capital creation, effective land control and management, reduction of cost associated with informal land transaction, and employments opportunities. Apart from the positive impacts, this ESMP also identified some negative implications associated with the proposed interventions, which need to be mitigated in order to ensure project acceptability and sustainability. Among the negative impacts are: Conflict over land use and land rights, ineligibility for some people to obtain CCROs, inequalities for women and other marginalized group, likely of emergence of gender-based violation, influx of laborers, soil erosion and dust, generation of waste, and health and safety hazards.

To address the aforementioned risks and impacts, the ESMP include a comprehensive Environmental and Social Management Plan (ESMP) and a Monitoring Plan for proper implementation of the project and reduction of the negative effects from the project. The MLHHD is committed to effect this ESMP through ensuring that enough budget, human resources and logistics are available.

## 7.3 Recommendations

- All Villages where the project is implemented should have the copy of this ESMP,

- NGOs to be hired to conduct certification process in Tanganyika District Council should be given this ESMP as part of the contract to ensure its implementations team in Tanganyika District Council with Support from ESMT

- PLUM (ES TEAM) shall ensure meaningful consultation of all key and relevant stakeholders

- Adequate budget should be allocated to facilitate implementation of the mitigation measures to avoid project impacts to the environment and the community and enhance project benefits.

- Training to all stakeholder on E&S issues is key for achieving the objectives of this ESMP. All key stakeholders identified in this ESMP must be trained to facilitate smooth implementation of the E&S issues during project implementation.

Appendix 1: Due Diligence in the Villages where there is Existing VLUP

| Sn | Checklist | Description |
| --- | --- | --- |
| 1 | Is the village land uses approved through village Assembly | - Conduct environmental and social assessment of the proposed land use plan basing on ESMF, ESCP, VGPF, SEP and RAP - Basing on 1 above, confirm if the plan complies with ESF - Check on supporting documents used to approve the VLUP (Entry Meeting Minutes and Approval of VLUP Meeting minutes) - Check on engagement of women, youth and other minority community members |
| 2 | Is the proposed land use compactible with the GN | - Check in the issues related to Reserve land and Village land - Check if there are land uses conflicts between different land users (Environmental Conservation vs land uses) |
| 3 | Is the VLUP endowed by District Council | - Check on District Statement on Regards to proposed land use (Normally written in a minute which are submitted to approval authorities for gazettement) |
| 4 | Is the VLUP Gazetted | - Confirm on gazettement status and if does not conflicting with other gazettement |

Note: The results from this table shall open a room for further discussion basing on different cases for proceeding with other rural certification process